## Mazen
Bug ID | Bug Title | Steps to proceed | Expected Result | Actual Result | Priority | Severity | Bug status | Related TC ID | Attachment
BUG_01 | Withdraw allows overdraft | POST withdraw > balance | 400 insufficient funds | Transaction accepted / or wrong behavior | High | Critical | Open | CT_03 | -
BUG_02 | API accepts amount as string | POST amount="abc" | Validation error | 500 / accepted incorrectly | Medium | Major | Open | CT_04 | -
BUG_03 | Negative amount accepted | Send amount=-100 | 400 invalid amount | Accepted | Medium | Major | Open | CT_05 | -
BUG_04 | Month=13 not validated | GET month=13 | 400 invalid month | API returns 200 | Low | Major | Open | MT_02 | -
BUG_05 | Date range reversed not rejected | GET from > to | 400 invalid range | API returns data | Medium | Major | Open | DR_02 | -
BUG_06 | Invalid date format not validated | GET wrong format | 400 invalid date | API still accepts | Low | Major | Open | DR_03 | -
BUG_07 | Wrong date format accepted | GET date="15-01-2024" | 400 invalid | 200 returned | Low | Major | Open | SD_03 | -
BUG_08 | Overdraft allowed in transfer | Transfer more than balance | 400 insufficient funds | Money deducted incorrectly | High | Critical | Open | TF_02 | -
BUG_09 | Transfer to invalid account accepted | POST to non-existing account | 404 not found | 201 created or no error | High | Major | Open | TF_03 | -
BUG_10 | Negative transfer amount accepted | amount<0 | 400 invalid | API accepts it | Medium | Major | Open | TF_04 | -
BUG_11 | Self transfer allowed | from==to | 400 error | Transfer succeeds | Medium | Major | Open | TF_05 | -

## Mostafa
Bug ID | Bug Title | Steps to proceed | Expected Result | Actual Result | Priority | Severity | Bug status | Related TC ID | Attachment

## Fayez
Bug ID | Bug Title | Steps to proceed | Expected Result | Actual Result | Priority | Severity | Bug status | Related TC ID | Attachment

## Adham
Bug ID | Bug Title | Steps to proceed | Expected Result | Actual Result | Priority | Severity | Bug status | Related TC ID | Attachment